## Cover Page
Airline Ticket Reservation System
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Academy Project Solutions
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog Airline Ticket Reservation System Project ID: A080 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role |  | Acceptance criteria | Priority | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
US_1 | Initial Selection | All Users - Admin, User | As Users we should have option to select our roles | 1-Screen should display the option to select Users role - Admin, User for login. 2- The Login page and the Home page should be displaying the recent news. | Critical | 1 | 2
US_2 | Admin Login | Admin | As an Admin I want to login to the system | 1-Admin should have option to select their role option 2-Admin should select the Admin option. 3-Admin's User id and password should be pre-loaded in the database, which can be used to log in. 4- Error Message "User id or Password is incorrect: should be displayed when a wrong User id or password is entered. | Critical | 1 | 5
US_3 | Admin Home page | Admin | As Admin I want to view my home page | 1- Home page should display "Welcom Admin" 2- The Login page and the Home page should be displaying the recent news. 3- Admin should have the following tabs dsiplayed in all pages for easy navigation Home, Manage flight, Schedule flight, Booking details,User Details, Logout 4-Clicking these tabs, Admin should be redirected to the corresponding pages | Critical | 1 | 2
US_4 | User Details | Admin | As Admin, I want to view user details | 1- Admin should click User Details tab to view all the user details who has registered in the system. User name, User Id, Email Id, Address,Ph Number can be fields listed | Critical | 1 | 2
US_5 | Manage Flights | Admin | As Admin, I want to add flights | 1- Admin on clicking Manage flight should be directed to Manage flight page. | Critical | 1 | 3
US_5a |  |  |  | 2- Admin should be listed with the flight details. 3- Admin should be able to view, update and add new flights | Critical | 2 | 5
US_5b |  |  |  | 4-Below are the fields to be listed for the admin to fill- Airlines Name Flight Number Flight Model - Selected from drop down Flight type - domestic,international - Drop down No of seats - should be updated for Economy and business class seperately 5- Submit button should be available, clicking which should validate each field and update the database while update and add flight details | Critical | 2 | 5
US_6 | Schedule flights | Admin | As Admin I want to schedule flights | 1-Schedule flight page should list all the flights available. 2-Admin should select the flight for which he want to update the schedule | Critical | 1 | 3
US_6a |  |  |  | 3- Admin on clicking the "Schedule" button, admin should fill the below details Source station - Drop down Destination- Drop down Departure time- Drop down Arrival time- Drop down Cost Days - should be listed in the form of checkbox, Sun - Sat, along with All option. Admin should select the days the flight will be available, For all days, he can select option All. | Critical | 2 | 5
US_6b |  |  |  | 4- Clicking Submit should schedule the flight as per Admin's input. | Critical | 2 | 5
US_7 | Booking Details | Admin | As Admin I want to view the booking details | 1- In the Booking Details page, admin should be displayed with all the booking details 2- Admin should select the flight number, date, source and destination. | Critical | 1 | 5
US_7a |  |  |  | 3- Based on the details given by the admin, details should be listed. 4-User name, User id, No of passengers etc should be displayed. | Critical | 2 | 3
US_8 | User Registration | User | As User, I want to register into the system | 1- User should have the Registration option in the login page 2-On Clicking the Register button, user should be taken to the registration page. | Critical | 1 | 3
US_8a |  |  |  | 3- Below are the fields user shoud be lidted Name- length should be 3-20 DOB- should be selected from the drop down calendar, Age >18 Gender - drop down password -length should be >=6, with special characters confirm password - Should be same as the password address Email id Adhar card- to be uploaded | Critical | 1 | 5
US_8b |  |  |  | 4 - On clicking the save button, all the fields should be validated as specified above. 5- Error messages should be displayed appropriately if any validation fails. 6- On Sucessfull validation, update the details in the DB and display the message "Updated successfully" | Critical | 2 | 5
US_9 | User Login | User | As User, I should be able to select my role | 1-User should have option to select their role option 2-User should select the User option. 3- Error Message "User id or Password is incorrect: should be displayed when a wrong User id or password is entered. | Critical | 1 | 5
US_10 | User Home page | User | As User, I want to navigate to home page | 1- Home page should display "Welcom User Name" 2- The Login page and the Home page should be displaying the recent news. 3- User should have the following tabs displayed in all pages for easy navigation Home, Book Tickets, View History, Logout 4-Clicking these tabs, user should be redirected to the corresponding pages | Critical | 1 | 2
US_11 | Book Tickets | User | As User, I want to book tickets | 1-User should select the date of travel, Source and destination. 2-All the flights available for that date with the mentioned source and destination should be deisplayed. | Critical | 1 | 5
US_11a |  |  |  | 3-The result should have - Flight name, number,no of seats available in economy and business class etc 4- User should select the flight he want to book | Critical | 1 | 5
US_11b |  |  |  | 5- It should display the fields User name, User id (auto populated from thelogin details), Source, destination, date and time of the flight taken from the flight details. | Critical | 2 | 5
US_11c |  |  |  | 6- User shoud select economy/business class and no of passenger travelling | Critical | 2 | 3
US_11d |  |  |  | 7- On entering the no of passengers travelling, User should be prompted to fill the details of the passenger - Passenger name, gender, age,Proof id 8-Clicking submit would take the user to Payment page | Critical | 2 | 3
US_12 | Payment | User | As User, I want to pay for tickets to confirm the booking | 1-On clicking the pay button, the total fare should be displayed. 2- The user should be provided with the mode of payment, Bank name, Card name options. 3- Payment can be mocked by having 4-5 account details saved in the database. Entering those details in the payment page, the amount should be deducted from the account | Medium
US_13 | Search Option | Admin/User | As Admin/User, I want to search flights | 1- Search option should be available for admin and user in schedule flight and book tickets page respectively. 2- Admin/User should be able to search based Flight number/ Flight name/Source and destination Note - use Pagenation to display the search results | Low
US_14 | Available seats | All | As Admin, I want to display only the available seats | 1-As the user books the tickets, the number of available seats, for the particular flight should be reduced accordingly. 2- The details should be displayed accordingly wherever available seat detail is displayed. | Critical | 2 | 5
US_15 | View History | Users | As User, I want to view the list of booking I have done in the past | 1- User should be displayed with the list of tickets they have booked so far 2- Date of travel, flight name, source, destination, no of passengers travelled ,travelled/cancelled status should be the details. | Medium | 2 | 5
US_16 | View Profile | Users | As User I want to view my details | 1-User should have a view profile tab clicking which should take them to view profile page. 2-Users details given during registration should be displayed here (except for password) 3-User should have Edit/update option, clicking which should allow the user to update their profile. 4-User id - should be a non editable field. Other fields can be edited. 5- Upon clicking Save button, should validated each field as validated during registration and saved successfully. 6- On any error should display appropriate error message. | Medium | 1 | 5
US_17 | View User details | Admin | As Admin I want to view user details | 1- Admin should be displayed with the user details in the user details page. 2- User id, User name, mobile number, Email id can be the details. | Low | 2 | 3
US_18 | Generate Report | Admin | As Admin I want to generate report | 1- Admin should have option to Generate report 2- Admin can select the list of details he want (For eg - flight number, flight name, source, destination etc) 3- Admin should have option to select from and To date. 4- Clicking generate report should display the fields selected by the Admin, for the period admin selected. 5-Admin should have option to download the result in the form of excel sheet | Low
US_19 | Create survey | Admin | As Admin, I want to create feedback questionarries | 1- Admin should have option to create questionnareis for user feedback. 2- 3 to 4 questions can be created by admin based on the service and travel experience. 3- Submitting the questions, it should be available for the users | Low
US_20 | User feedback | User | As User, I want to submit feedback | 1- User should have option to update feedback 2- The questionarries created by the admin should be displayed. 3- Clicking submit should validate the user input and submit it. 4- For any validation errors, Appropriate message should be displayed | Low
US_21 | Survey results | Admin | As Admin, I want to view survey results | 1- Admin should be able to view the feedback updates given by the users. 2- This can be downloadable in excel format | Low
US_22 | Forgot password | All Users - Admin, User | As User I want the system to have Forget Password option. | 1-When the user clicks Forgot Password, system should ask for the User ID and secret questions. Email id and contact number can also be used along with the secret questions to uniquely identify the User as Same answers can be given by many users 2-On answering the questions correctly, the password reset page should be displayed. 3-On entering the details in the password reset page, password should be validated 4-On clicking Submit, the details should be saved to the Database | Low
US_23 | Log out | All Users - Admin, User | As users, we want to log out of the application. | 1- When the users logs out the user session data should be cleared and redirected to the login page with the message "user successfully logged out". | Critical | 2 | 5

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000